## Sheet1
Hallwaybot - Timeline |  |  | 2017
|  |  | MAY |  |  |  | JUNE |  |  |  | JULY
Deliverables |  | Duration | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
Planning phase |  | 2w
| Team Formation | 1w
| Brainstorming of Ideas | 2w
| Distributing of tasks | 1w
Design phase |  | 4w |  |  | 1
| Architecture Design | 2w
| Detailed Design | 2w
| Documentation | 4w
Implementation phase |  | 4w | [7 empty] | 2
| Coding & (Infield-)Testing | 3w
| (Further Enhancements) | 1w
| Documentation | 4w
Closure Phase |  | 4w | [10 empty] | 3 | 4
| Demo Preparation | 4w
| Report Preparation | 3w
| Self Evaluation | 1w
Annotations |  |  | 1 |  | May 19th (Fr) |  | Design Milestone Presentations
|  |  | 2 |  | June 30th (Fr) |  | Project Intermediate Presentations
|  |  | 3 |  | July 21st (Fr) |  | (Final Review)
|  |  | 4 |  | July 24th (Mo) |  | Project Final Presentations